## Product Backlog
ID | As a/an | I want to | So that | Priority | Status | Added in Sprint | Story Point
1 | Admin | view all courses (by year, by faculties...) | i can manager and follow courses |  |  | :)
|  | view a course's detail | i can get more exactly information about the course |  |  | :)
3 |  | add, edit, disable a course | i can update a new course or modify an old course |  |  | :)
4 |  | search courses | i can easily manager and follow courses |  |  | :)
5 |  | view all staffs (by role, by name...) | i can manager and follow staffs |  |  | :)
6 |  | view a staffs detail | i can get more exactly information about the staff |  |  | :)
7 |  | add,edit,delete a staff | i can update a new staff or modify an old staff |  |  | :)
8 |  | search staffs | i can easily manager and follow staffs |  |  | :)
9 |  | add, edit, disable role's access | i can update a new role's access or modify an old role's access |  |  | :)
10 | Course Leader (CL) | have a form to fill a CMR for each course | i can easily insert report information to the CMR |  |  | :)
11 |  | auto email an copy of CMR | it is faster and more convinient for approval |  |  | :)
12 |  | view CMRs until they are approved | i can manager my CMRs if anything is wrong util they are approved |  |  | :)
13 | Course Moderator (CM) | auto email an copy of CMR after I approved | view all approved CMRs for all Faculties |  |  | :)
14 | Director of Learning and Quality (DLT) | view all approved CMRs for all Faculties | i can manager and follow the CMR to improve courses |  |  | :)
15 |  | have a form to comment a CMR and auto sent to CL, CM, PVC | i can comment on a selected CMR that has been approved |  |  | :)
16 |  | have a function to notify me to comment a CMR if 14 days is nearly end | i don't forget to comment any CMR |  |  | :)
17 | Pro-Vice Chancellor (PVC) | view all approved CMRs for all Faculties | i can manager and follow the CMR to improve courses |  |  | :)
18 | Guest | view approved CMRs list (by course, by year...) | I can get information of all courses |  |  | :)
19 |  | view an approved CMR's detail | i can get more exactly information about the course |  |  | :)
20 |  | view statistical, and exception report list (by course, by year...) | I can select the report i want |  |  | :)
21 |  | view a statistical report detail | I can know the detail of that report |  |  | :)
22 |  | view exception report list | I can select the report i want |  |  | :)
23 |  | view a exception report detail | I can know the detail of that report |  |  | :)
24 | System | i want the interface must be suitable for all devices | it helper user easily use system |  |  | :)

## Sprint 1
Sprint | Sprint Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
1 | view all courses (by year, by faculties...) | Create Database | Nghia, Tuan Son | Done | 3 | 3 | 0 | 0 | 0
|  | UI Design | Son, Ha | Done | 4 | 2 | 1 | 1 | 0
|  | Code back end | Son | Done | 3 | 2 | 1 | 1 | 1
| Create course and assign to a CL | UI Design |  | Not Started | 4 | 2 | 1 | 1 | 0
|  | Code back end |  | Not Started | 4 | 2 | 1 | 1 | 0
|  | Total |  |  | 18 | 11 | 4 | 4 | 1 | 0

## Sprint2
Sprint | Sprint Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
2 | have a form to fill a CMR for each course | UI Design | SonN, Ha | Done | 6 | 2 | 3 | 1 | 0
0
|  | Ingeration |  | Processing |  |  |  |  | 1
|  | Code back end | Nghia | Done | 5 | 2 | 3 | 0 | 0
| view CMRs until they are approved | UI Design | SonN | Not Started | 4 |  |  |  | 4
|  | Code back end | Phuc | Not Started | 4 |  |  |  | 4
| Update all interface | update interface | SonN | [5 empty] | 3
| Create course and assign to a CL | UI Design Total Layout | SonN | Done | 4 | 2 | 1 | 1 | 0
|  | UI Design Input | Phuc | Done | 2 | 1 | 0 | 0 | 0
|  | Code back end | Phuc | Done | 4 | 2 | 1 | 1 | 0
| Edit Create CMR (add button create CMR) |  |  |  |  | 9 | 8 | 3 | 12
|  | Total |  |  | 19 | 4 | 6 | 1 | 24 | 0

## Sprint3
Sprint | Sprint Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
3 | have a form to fill a CMR for each course | UI Design | SonN, Ha | Done | 6 | 2 | 2 | 1
|  | Ingeration | SonN, Phuc | Done | 6 | 6 | 4 | 2 | 0
| Update UI | UI CMR | SonN | Donne | 4 | 2 | 2 | 0 | 0
|  | UI Add New | SonN | Done | 4 | 2 | 2 |  | 0
| General Fixes | CMR Data (Faculty) | Nghia | Done | 1 | 0 |  |  | 0
|  | Database | Nghia | Done | 2 | 1 | 0 |  | 0
| Code Backend | View CMR | Phuc | Done | 1 | 0 |  |  | 0
|  | View Course Detail | Phuc | Done | 1 | 0 |  |  | 0
[7 empty] | 10 | 3
[5 empty] | 25 | 13

## Sprint 4
Sprint | Sprint Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
4 | As a Course Leader, I want to have a form to fill a CMR for each course | UI CMR Detail | Ha | Done | 1
|  | Integrate ui CMR detail with backend | Phuc | Done | 1 | 1 | 1 | 1 | 1
|  | UI List CMR | SonN | Done | 3
| CM | Auto Sending E-mail |  | Not Started
|  | Sending email method | Phuc | Done | 2
|  | View approved CMR backend | Nghia | Done | 2 | 2 | 2 | 1 | 0 | 0
| Security | Encrypted Password | Phuc | Done | 2
| Login | Check Role Login | Nghia | Done | 1 | 1 | 1 | 0 | 0 | 0
| Course | UI Assign course to CL CM | SonN | Done | 4 | 3 | 2 | 1
|  | Assign course to CL CM backend | Nghia | Done | 2 | 2 | 2 | 1 | 1 | 0
|  | CL can view Course assigned backend | Nghia | Processing | 2 | 2 | 2 | 2
[5 empty] | 20 | 11 | 10 | 6 | 2

## Sprint 5
Sprint | Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
5 | Course | CL can view Course assigned backend | Nghĩa | Done | 1 | 1 | 1 | 0 | 0
| As an CM, I want to auto email an copy of CMR after I approved | Auto send email when submitted | Phúc | Done | 2
| As an admin, I want to search courses | Find course (backend) | Nghĩa | Done | 1 | 1 | 1 | 1 | 0
|  | UI search | Hà | Done | 1
| As an admin, I want check role | Check role (backend) | Nghĩa | Done | 1 | 1 | 1 | 0 | 0
| As a PVC, I want to view approved CMR | View (backend) | Nghĩa | Done | 1 | 1 | 1 | 1 | 0
| As an admin, I want add account | Add UI | SonN | Done | 2 | 2 | 1 | 1 | 0
|  | Backend | Phúc | Done | 3 |  |  | 1
[5 empty] | 12 | 6 | 5 | 4 | 0

## Sprint 6
Sprint | Backlog Item | Task | Volunteer | Status | Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Sprint Review
6 | Admin | view a staffs detail | Phuc | Processing
|  | edit,delete a staff | Phuc | Done | 4 | 4 | 2 | 0 | 0
|  | search staffs | Phuc | Done | 2 | 2 | 2 | 1 | 0
|  | UI | SonN | Processing
| Director of Learning and Quality (DLT) | view all approved CMRs | Nghia |  | 1 | 0 | 0 | 0 | 0 | 0
|  | form to comment a CMR and auto sent to CL, CM, PVC |  | NOT STARTED
|  | Auto email sent for time-expired notification | Phuc | NOT STARTED
|  | View Approved CMR Back end | Nghia | Done | 1 | 0 | 0 | 0 | 0 | 0
|  | Comment on CMR UI | SonN | Processing
|  | View CMR Details UI | SonN | Processing
| System | Suitable UI for Mobile | All | Done
| As an admin, I want add account | Interate | Phúc | Processing
| System Session | Logout Button + Backend | Nghia | Done | 1 | 0 | 0 | 0 | 0 | 0
| Report System | Statistical SQL Backend | Nghia | Done | 3 | 3 | 3 | 3 | 2 | 1
|  | Exceptional SQL Backend | Nghia | Done | 2 | 2 | 2 | 2 | 1 | 0
[5 empty] | 14 | 11 | 9 | 6 | 3

## Burndown chart
Project | Task |  | Week 9 | Week 8 | Week 7 | Week 6 | Week 5 | Week 4 | Week 3 | Week 2 | Week 1
Meeting 1 | Database Design | Day 1 | 6 | 7 | 9 | 13 | 11 | 9 | 6 | 4 | 7
Meeting 2 | Sprint 1 | Day 2 | 0 | 7 | 8 | 10 | 10 | 1 | 3 | 3 | 4
Meeting 3 | Sprint 2 | Day 3 | 0 | 0 | 3 | 3 | 6 | 4 | 1 | 2 | 3
Meeting 4 | Sprint 3 | Day 4 | 0 | 4 | 0 | 4 | 2 | 4 | 1 | 3 | 4
Meeting 5 | Sprint 4 | Ideal Worktime | 153 | 135 | 115 | 90 | 65 | 45 | 30 | 15 | 0
Meeting 6 | Sprint 5 | Actual Worktime | 155 | 138 | 118 | 88 | 59 | 41 | 30 | 18 | 0
Meeting 7 | Sprint 6
Meeting 8 | Statistical report
Ideal Worktime
Actual Worktime